## Sheet1
Risk No. | Risk | Description | Hazard | Likelihood | Impact | Solution | Update
Time Management
1.1 | Not starting my project on time | Failing to start creating my project in a timely fashion and leaving it late | By starting my project late, I would risk falling behind which would lead to rushing my project resulting in a lower quality of work or even failing the assessment | 2 | 5 | Use the Trello board I created to meet deadlines I have set myself to ensure that I complete tasks and stay ahead. Additionally, use the document provided in the '#important' channel on Slack to know what I should have done at the end of each week as a minimum | 1. I have managed my time well so far, staying on top of the workload
1.2 | Being distracted by social events | Instead of spending time working on my project, I go out drinking/eating/partying/socializing etc. | Over-socilaizing could result in failing to meet deadlines or impacting my working negatively due to headache, tiredness, lack of motivation and so on | 2 | 5 | Focus on my work and do not socialize OR alternatively, get a sufficient amount of work completed daily to meet deadlines allowing myself to have a healthy balance of working and socializing | 1. Due to the current situation in the UK this risk has been minimized
Common Computer-related Injuries And Problems
2.1 | Common injuries: mouse shoulder, computer back, carpal tunnel sundrome, lumar sprains and strains, disc injuries & tennis elbow | The forementioned Injuries could happen if I spend too much time sat at computer for too long | Incurring these injuries would lead to not being able to use my computer or PC at the office resulting in lost time working on the assessment | 1 | 4 | Arranging my desk to promote good posture, add support, fet up often & exercise | 1. My desk arrangement is set out comfortably, no injuries to report
2.2 | Eye Strain | Looking at my laptop, PC, phone or other digital device for uninterrupted periods of time | Eye fatigue and discomfort, dry eyes, headache, blurred vision, neck and shoulder pain, eye switching & red eyes | 3 | 4 | Use proper lighting, minimise glare, adjust computer display settings, take frequent breaks & consider computer glasses
2.3 | Sleeping Problems | Issues sleeping due to the artificial lighting from laptop or PC screens | The unnatural lighting suppresses the release of melatonin - the substance that assists sleeping patterns. Not having a routine sleeping pattern could result in bad performance while working on the assessment | 2 | 4 | Refrain from using a computer before going to sleep. Perhaps even resort to reading a book or something to that degree so that falling asleep may become easier
Security
3.1 | SQL injection attacks | A very common code injection technique that might destroy my database | This usually occurs when a user is asked for an input, and instead of giving you the required input the user will give a statement that you will unknowing run on your database, possibly destroying or stealing data etc. | 2 | 4 | Using Flask-SQLAlchemy will reduce the risk since it does not deal with the input of raw SQL | 1. I have been working safely and securely, no security breaches to report
3.2 | Operating on Unsecure Networks | When working on my project on unsecure networks, there is a possibility that applications such as Command-line Interfaces (CLI), Visual Studio Code, Google Cloud Platform (GCP) and so on, are vulnerable to various types of hacking | If any application I am using to complete my project is hacked, my work could be ruined or destroyed, which is obviously hazardous as this will affect my mark for the project | 1 | 4 | Use Secure Shell (SSH), a cryptographic network protocol, to encrypt passwords and files etc. to ensure confidentiality and integrity over my data. Also, do not upload credentials such as private keys to my GitHub Repository
3.3 | Distributed Denial-of-service (DDoS) Attacks | A cyber-attack in which a hacker seeks to make a machine or network resource unavailable to its intended users by disrupting services of a host connected to the internet | The web-server my project is hosted on becomes flooded with internet traffic making it difficult or impossible for user requests to be processed, thus disrupting the use of my CRUD application through the HTML front-end | 1 | 4 | Take several security measures, such as securing network infrastructure, practice basic network security, scan for unusual activity, leveraging the cloud or even installing anti DDoS hardware and software
Other
4.1 | Going over my free GCP money limit | When you first set up an account on Google Cloud Platform (GCP) you are given $300 (£230) of free money over a year in order to use Virutal Machines (VM) that enable you to connect applications to a separate machine that is virtual. However, there is a fee for using these machines hence the free money to begin with | The VMs will be used during the first SFIA project. The free money should cover the cost of using VMs, however if the VM instance is left running when not in use there is the hazard I could go over the limit and charges will incur on my personal bank card | 3 | 5 | Ensure that when not needed, the VMs are stopped so that the free money will not be used when there is no need for it to be. Esssentially, start and stop the VM instance when and when not in use | 1. There is plenty money left on my GCP account because of stopping VMs when they are not needed
4.2 | Not understanding a topic covered in class | When in training, not comprehending a subject or concept that is being taught to me | If I am unable to understand what I am meant to be learing, then I am at risk of getting something wrong in the assessment that I am going to be graded on which could affect my overall result | 3 | 4 | This could be likely as I am learning new ideas and concepts, however as long as I participate and ask questions when I am stuck I should be able to grasp what I am being taught. Additionally, doing extra work outside of office hours will be very benefical | 1. Through asking questions when needed and 1-2-1 discussions with my trainer(s), I have managed to understand all topics covered so far